## Sheet1
N0. | Task Details | Owner | Start | Finsh | Progress | Status | Risks/ Issues | Comments
| DataBase | Eng Team -> Carloine | 2017-01-02 | 2017-01-08 | 0% | Pending | Legal, Privacy
1 | Requirments
1.1 | Meeting |  | 2017-01-02 | 2017-01-02 | 100% | Completed
1.2 | Prelimanary Draft |  | 2017-02-02 | 2017-03-02 | 100% | Completed
1.3 | Review |  | 2017-04-02 | 2017-05-02 | 100% | Completed
1.4 | Draft Expantion |  | 2017-06-02 | 2017-12-02 | 100% | Completed
1.5 | Review |  | 2017-12-02 | 13/2/2017 | 100% | Completed
2 | Data Protype
2.1 | Basic ER Design |  | 14/2/2017 | 20/2/2017 |  | Pending
2.2 | Review |  | 21/2/2017 | 23/2/2017 |  | Pending
2.3 | ER detail Design |  | 24/2/2017 | 2017-12-03 |  | Pending
2.4 | Review |  | 13/3/2017 | 16/3/2017 |  | Pending
2.5 | Fully Develop ER Design |  | 17/3/2017 | 2017-04-04 |  | Pending
2.6 | Prepare Tech Report For Development |  | 2017-05-04 | 2017-08-04 |  | Pending
3 | Development 1 : Planning
3.1 | Project Planning (Dev Team, Arc's, Analyst etc.) |  | 2017-09-04 | 2017-10-04 |  | Pending
3.2 | Data Flow(Tech) |  | 2017-11-04 | 15/04/17 |  | Pending
3.3 | Work Flow(Managment) |  | 2017-11-04 | 15/4/2017 |  | Pending
3.4 | GUI (Design) |  | 2017-11-04 | 15/4/2017 |  | Pending
3.5 | System Architecture (Arc's) |  | 2017-11-04 | 15/4/2017 |  | Pending
3.6 | Quality Assurance, Legal (Managers) |  | 2017-11-04 | 15/4/2017 |  | Pending
4 | Development 2: Building
4.1 | Build Componat 1 |  | 16/4/2017 | 18/5/2017 |  | Pending
4.2 | Unit Testing Componant 1 |  | 19/5/2017 | 22/5/2017 |  | Pending
4.3 | Build Componat 2 |  | 24/5/2017 | 14/6/2017 |  | Pending
4.4 | Unit Testing Componant 2 |  | 15/6/2017 | 17/6/2017 |  | Pending
4.5 | Build Componat 3 |  | 18/6/2017 | 28/7/2017 |  | Pending
4.6 | Unit Testing Componant 3 |  | 29/7/2017 | 2017-02-08 |  | Pending
5 | Testing
5.1 | Create Test Plan |  | 2017-04-07 | 2017-08-07 |  | Pending
5.2 | Create Test Cases |  | 2017-09-07 | 2017-11-07 |  | Pending
5.3 | Execute Test Case Round - 1 |  | 13/7/2017 | 16/7/2017 |  | Pending
5.4 | Record Defects Round - 1 |  | 17/7/2017 | 18/7/2017 |  | Pending
5.5 | Fix Defects |  | 20/7/2017 | 24/7/2017 |  | Pending
5.6 | Execute Test Case Round - 2 |  | 26/7/2017 | 30/7/2017 |  | Pending
5.7 | Record Defects Round - 2 |  | 2017-01-08 | 2017-02-08 |  | Pending
5.8 | Draft Testing Report |  | 2017-04-08 | 2017-10-08 |  | Pending
6 | User Acceptance
6.1 | Draft UAT Test Cases |  |  |  |  | Pending
6.2 | Perform UAT - Round 1 |  |  |  |  | Pending
6.3 | Record Defects |  |  |  |  | Pending
6.4 | Fix Defects |  |  |  |  | Pending
6.5 | Perform UAT - Round 2 |  |  |  |  | Pending
7 | Deploy
7.1 | Draft deployment plan |  |  |  |  | Pending
7.2 | Dry Run deployment |  |  |  |  | Pending
7.3 | Fix Dry Run Observations |  |  |  |  | Pending
7.4 | Implement Production |  |  |  |  | Pending
8 | Go Live